## Dashboard
SAFETYRAG ¦ DISSERTATION MASTER PLAN
Dependency-ordered research, engineering, experiments, publications and graduation ¦ Baseline 2026-10-29
TOTAL TASKS |  | COMPLETED (DOCUMENTED) |  | IN PROGRESS | IMPLEMENTED / VERIFY
177 |  | 0 |  | 41 | 10
STATUS | COUNT |  | RESEARCH AREA | TASKS
Not Started | 119 |  | Governance | 9
In Progress | 41 |  | Literature | 10
Implemented—Verify | 10 |  | Methodology | 9
Needs Verification | 5 |  | Engineering | 28
Completed (Artifact) | 1 |  | Architecture | 8
Completed (Analysis) | 1 |  | Case Study | 18
Completed (Verified) | 0 |  | Integration | 7
Blocked | 0 |  | Evaluation | 22
|  |  | Human Study | 14
|  |  | Publication | 22
|  |  | Dissertation | 13
STATUS INTERPRETATION: A completed draft or implemented feature is NOT equivalent to a verified dissertation result. |  |  | Graduation | 9
|  |  | Management | 8
WORKFLOW: Master Checklist → prerequisite IDs → deliverable → verification evidence → update status → Phase Roadmap

## Master Checklist
Task ID | Phase # | Phase / Milestone | Workstream | Task / Activity | Detailed goal and completion criteria | Expected output / deliverable | Current status | Priority | Prerequisite task IDs | Owner / responsible | Evidence / output location | Status evidence / confidence | Blocker / next action | Notes / committee decisions
01.01 | 1 | Research governance and approval | Governance | Consolidate authoritative research scope | Reconcile the dissertation proposal, architecture paper, committee presentation, MCAS case-study plan and current software state; record which claims are planned versus verified. | Approved research scope and document register | In Progress | High |  |  |  | Prior implementation or draft; verification required
01.02 | 1 | Research governance and approval | Governance | Identify supervisory and committee roles | Confirm adviser, committee membership, decision rights, institutional forms and meeting cadence; document unresolved administrative requirements. | Committee and approval responsibility matrix | Needs Verification | High | 01.01 |  |  | Prior implementation or draft; verification required
01.03 | 1 | Research governance and approval | Governance | Finalize dissertation research problem | Specify the software-safety engineering failure modes addressed, users, artifact types, operating assumptions and excluded certification claims. | Problem statement and scope boundaries | In Progress | High | 01.01 |  |  | Prior implementation or draft; verification required
01.04 | 1 | Research governance and approval | Governance | Map contributions to doctoral standards | Translate proposed architecture, empirical methods, reproducibility and case-study contributions into dissertation-level criteria. | Contribution-to-evidence matrix | In Progress | High | 01.03 |  |  | Prior implementation or draft; verification required
01.05 | 1 | Research governance and approval | Governance | Update committee presentation for REFSafE | Incorporate the Das et al. comparator, revised novelty claims, updated research questions and strong baseline into committee materials. | 41-slide updated presentation and speaking script | Completed (Artifact) | High | 01.03 |  |  | Existing artifact / earlier work
01.06 | 1 | Research governance and approval | Governance | Conduct proposal rehearsal and challenge review | Run mock Q&A on novelty, validity, MCAS hindsight bias, safety claims, scope and feasibility; revise weak arguments. | Rehearsal issue log and revised slides | Not Started | High | 01.05 |  |  | Planned / not evidenced
01.07 | 1 | Research governance and approval | Governance | Present proposal to committee | Deliver the research-approval presentation and document feedback, conditions and requested revisions. | Committee meeting record and action list | Needs Verification | High | 01.06 |  |  | Prior implementation or draft; verification required
01.08 | 1 | Research governance and approval | Governance | Obtain documented proposal approval | Resolve committee conditions and obtain the institution's formal approval before treating the proposal as authorized. | Signed/recorded research approval | Needs Verification | High | 01.07 |  |  | Prior implementation or draft; verification required
01.09 | 1 | Research governance and approval | Governance | Create change-control register | Track deviations from approved research questions, experiments, data sources and participant protocols with rationale and approvals. | Research change log | Not Started | High | 01.08 |  |  | Planned / not evidenced
02.01 | 2 | Prior art, novelty and theory | Literature | Consolidate systematic search protocol | Define databases, search strings, date limits, screening criteria, inclusion/exclusion and reproducible export formats. | Search protocol and query log | In Progress | Medium | 01.03 |  |  | Prior implementation or draft; verification required
02.02 | 2 | Prior art, novelty and theory | Literature | Build de-duplicated citation library | Collect DOIs, versions, full texts, metadata and stable URLs; normalize references and remove duplicates. | BibTeX/Zotero master library | In Progress | Medium | 02.01 |  |  | Prior implementation or draft; verification required
02.03 | 2 | Prior art, novelty and theory | Literature | Complete REFSafE full-text extraction | Extract actual retrieval stages, datasets, human review, metrics, limitations and differences from SafetyRAG without inferring missing features. | Evidence-coded REFSafE comparison | Completed (Analysis) | Medium | 02.02 |  |  | Existing artifact / earlier work
02.04 | 2 | Prior art, novelty and theory | Literature | Review closest 2024–2026 systems in full text | Evaluate REFSafE, STPA-LLM, aviation graph RAG, engineering-risk graph RAG, human-in-loop FHA and assurance-case systems. | Prior-art extraction matrix with citations | In Progress | Medium | 02.02 |  |  | Prior implementation or draft; verification required
02.05 | 2 | Prior art, novelty and theory | Literature | Review safety engineering foundations | Ground the work in STAMP/STPA, FMEA, FTA, hazard logs, safety constraints, assurance cases, and relevant standards. | Safety theory and terminology chapter | In Progress | Medium | 02.02 |  |  | Prior implementation or draft; verification required
02.06 | 2 | Prior art, novelty and theory | Literature | Review retrieval and verification foundations | Cover BM25, vector/hybrid/graph retrieval, provenance models, temporal retrieval, entailment, RAG evaluation and uncertainty. | Methods background and citation set | In Progress | Medium | 02.02 |  |  | Prior implementation or draft; verification required
02.07 | 2 | Prior art, novelty and theory | Literature | Code literature capabilities conservatively | Use reported/partial/not established rather than claiming competitors cannot do unreported functions; track source pages. | Auditable comparative feature matrix | In Progress | Medium | 02.03;02.04 |  |  | Prior implementation or draft; verification required
02.08 | 2 | Prior art, novelty and theory | Literature | State bounded and falsifiable novelty | Distinguish integrated safety-typed evidence, version/time eligibility, claim verification and authorized acceptance from existing RAG features. | Novelty statement and threat-of-priority analysis | In Progress | Medium | 02.07 |  |  | Prior implementation or draft; verification required
02.09 | 2 | Prior art, novelty and theory | Literature | Complete citation chaining and independent review | Backward/forward citation chasing and second-reader screening; document disagreements and missed work. | Search coverage and screening report | Not Started | Medium | 02.04 |  |  | Planned / not evidenced
02.10 | 2 | Prior art, novelty and theory | Literature | Freeze literature snapshot for proposal/paper | Archive search results and coding decisions; plan scheduled update before manuscript submission and defense. | Versioned literature review dataset | Not Started | Medium | 02.09 |  |  | Planned / not evidenced
03.01 | 3 | Research questions, hypotheses and measurement | Methodology | Freeze research questions and hypotheses | Define RQ1 SEG, RQ2 retrieval, RQ3 claim verification, RQ4 human outcomes, RQ5 generalization; specify directional and null hypotheses. | RQ/Hypothesis register | In Progress | High | 01.08;02.08 |  |  | Prior implementation or draft; verification required
03.02 | 3 | Research questions, hypotheses and measurement | Methodology | Operationalize constructs and outcomes | Define evidence recall, relation-path recall, anchor correctness, unsupported claims, temporal leakage, hazard coverage and human outcomes. | Measurement dictionary | Not Started | High | 03.01 |  |  | Planned / not evidenced
03.03 | 3 | Research questions, hypotheses and measurement | Methodology | Predefine primary versus secondary metrics | Prevent post hoc metric shopping; specify aggregation, denominators, failure handling, severity weighting and acceptable uncertainty. | Metric specification and analysis plan | Not Started | High | 03.02 |  |  | Planned / not evidenced
03.04 | 3 | Research questions, hypotheses and measurement | Methodology | Specify experimental units and sampling | Define queries, artifacts, hazard tasks, work plans, participants, cases, repeated measures and cluster dependencies. | Sampling and unit-of-analysis plan | Not Started | High | 03.02 |  |  | Planned / not evidenced
03.05 | 3 | Research questions, hypotheses and measurement | Methodology | Write protocol for baseline and ablations | Specify identical model, corpus, prompt budget, retrieval budget, hardware, settings and stopping rules for all conditions. | Controlled experiment protocol | Not Started | High | 03.03 |  |  | Planned / not evidenced
03.06 | 3 | Research questions, hypotheses and measurement | Methodology | Predefine statistical analysis | Select confidence intervals, paired comparisons, effect sizes, multiple-testing handling, bootstrap/randomization and missing data. | Statistical analysis plan | Not Started | High | 03.04;03.05 |  |  | Planned / not evidenced
03.07 | 3 | Research questions, hypotheses and measurement | Methodology | Develop validity and ethics threat register | Document hindsight leakage, evaluator bias, incomplete evidence, case representativeness, LLM judge bias and model drift. | Threats-to-validity and mitigations register | In Progress | High | 03.01 |  |  | Prior implementation or draft; verification required
03.08 | 3 | Research questions, hypotheses and measurement | Methodology | Pre-register protocol where appropriate | Archive hypotheses, metrics, inclusion criteria and analyses before confirmatory runs; document exploratory deviations. | Time-stamped protocol/preregistration | Not Started | High | 03.06;03.07 |  |  | Planned / not evidenced
03.09 | 3 | Research questions, hypotheses and measurement | Methodology | Define stop/go gates and quality thresholds | Specify conditions for dataset readiness, feature conformance, reproducibility, human-study launch and submission. | Stage-gate acceptance checklist | Not Started | High | 03.03;03.07 |  |  | Planned / not evidenced
04.01 | 4 | Repository, infrastructure and reproducibility | Engineering | Inventory backend, frontend and MCAS repositories | Record actual repository URLs, branches, modules, build commands, versions, owners, secrets and missing source packages. | Repository and environment inventory | In Progress | Medium | 01.01 |  |  | Prior implementation or draft; verification required
04.02 | 4 | Repository, infrastructure and reproducibility | Engineering | Record verified toolchain versions | Verify Java release 21 build target, observed Spring Boot 4.1.1, Maven, PostgreSQL, Node/npm and React toolchain against current manifests. | Locked toolchain/version matrix | In Progress | Medium | 04.01 |  |  | Prior implementation or draft; verification required
04.03 | 4 | Repository, infrastructure and reproducibility | Engineering | Build backend on clean machine | Clone source, configure environment, resolve Maven dependencies, run clean verify and start Spring Boot without local assumptions. | Fresh-machine backend build log | Not Started | Medium | 04.02 |  |  | Planned / not evidenced
04.04 | 4 | Repository, infrastructure and reproducibility | Engineering | Build frontend on clean machine | Install pinned Node dependencies, run typecheck/tests/production build, validate environment configuration and API routing. | Fresh-machine frontend build log | Not Started | Medium | 04.02 |  |  | Planned / not evidenced
04.05 | 4 | Repository, infrastructure and reproducibility | Engineering | Reconstruct PostgreSQL database reproducibly | Provision empty database, apply ordered Flyway migrations, check schema invariants and verify repeatable startup. | Database bootstrap and migration transcript | In Progress | Medium | 04.02 |  |  | Prior implementation or draft; verification required
04.06 | 4 | Repository, infrastructure and reproducibility | Engineering | Prepare safe configuration and secret handling | Create sanitized env examples, credentials rotation, local AI configuration and no-secret commit checks. | Configuration templates and secrets policy | Not Started | Medium | 04.03;04.04 |  |  | Planned / not evidenced
04.07 | 4 | Repository, infrastructure and reproducibility | Engineering | Automate CI build, tests and linting | Create reproducible backend/frontend workflows with static analysis, migrations and artifact retention. | CI workflow and status badge | Not Started | Medium | 04.03;04.04;04.05 |  |  | Planned / not evidenced
04.08 | 4 | Repository, infrastructure and reproducibility | Engineering | Package runnable research release | Provide versioned build, checksums, seed fixtures, installation README and reproducibility scripts. | Tagged release and installation package | Not Started | Medium | 04.06;04.07 |  |  | Planned / not evidenced
04.09 | 4 | Repository, infrastructure and reproducibility | Engineering | Establish experiment configuration capture | Log git SHA, prompts, model ID, seed, embedding index version, hardware, data cutoff and feature flags per run. | Machine-readable run manifest | Not Started | Medium | 04.07 |  |  | Planned / not evidenced
05.01 | 5 | SafetyRAG core platform completion | Engineering | Confirm authentication and project workspace | Regression-test registration/login/JWT, project isolation, role permissions, project lifecycle and navigation. | Auth/project regression report | Implemented—Verify | Medium | 04.03;04.05 |  |  | Prior implementation or draft; verification required
05.02 | 5 | SafetyRAG core platform completion | Engineering | Validate document ingestion and versions | Test real PDF upload, extraction, metadata, revisions, duplicate handling, failures and download fidelity. | Versioned document ingestion acceptance tests | Implemented—Verify | Medium | 05.01 |  |  | Prior implementation or draft; verification required
05.03 | 5 | SafetyRAG core platform completion | Engineering | Validate evidence chunks and stable anchors | Ensure source spans, page/section locators, content hashes and re-indexing stability; preserve immutable historical versions. | Anchor resolution conformance suite | Not Started | Medium | 05.02 |  |  | Planned / not evidenced
05.04 | 5 | SafetyRAG core platform completion | Engineering | Validate requirements and system-model workflows | Exercise requirement import/edit, architecture components, associations, project scoping and traceability. | Requirements/model test fixtures | Implemented—Verify | Medium | 05.01 |  |  | Prior implementation or draft; verification required
05.05 | 5 | SafetyRAG core platform completion | Engineering | Validate SEG node and edge lifecycle | Test node/edge types, relation constraints, orphan prevention, duplicate handling, provenance and review status. | SEG schema and API contract tests | Implemented—Verify | Medium | 05.03;05.04 |  |  | Prior implementation or draft; verification required
05.06 | 5 | SafetyRAG core platform completion | Engineering | Validate AI extraction and SEG synchronization | Measure extracted entity/edge accuracy, provenance completeness, synchronization idempotency and reviewer control. | AI extraction and sync test report | Implemented—Verify | Medium | 05.05 |  |  | Prior implementation or draft; verification required
05.07 | 5 | SafetyRAG core platform completion | Engineering | Validate hazard and control analysis services | Test hazard generation, missing controls, STPA/FMEA/FTA integration points, project scope and result persistence. | Safety analysis API integration tests | Implemented—Verify | Medium | 05.05 |  |  | Prior implementation or draft; verification required
05.08 | 5 | SafetyRAG core platform completion | Engineering | Validate findings and human review workflow | Exercise stored runs, quotations, citation checks, accept/reject decisions, reviewer identity and cross-run summaries. | Finding/review acceptance test suite | Implemented—Verify | Medium | 05.06;05.07 |  |  | Prior implementation or draft; verification required
05.09 | 5 | SafetyRAG core platform completion | Engineering | Enforce authorization and immutable audit events | Prove AI cannot self-accept; unauthorized transitions fail; edits preserve history and evidence snapshots. | RBAC/state-machine invariant tests | Not Started | Medium | 05.08 |  |  | Planned / not evidenced
05.10 | 5 | SafetyRAG core platform completion | Engineering | End-to-end platform acceptance | From new project through upload, SEG, analysis, evidence inspection and review, run with no developer intervention. | End-to-end acceptance report and demo | Not Started | Medium | 05.02;05.06;05.08;05.09 |  |  | Planned / not evidenced
06.01 | 6 | Formal evidence model and guarantees | Architecture | Specify SEG ontology and typed signatures | Define node/edge kinds, allowable endpoints, identity, multiplicity, relationship meaning and integrity constraints. | Formal SEG schema and examples | In Progress | Medium | 02.05;05.05 |  |  | Prior implementation or draft; verification required
06.02 | 6 | Formal evidence model and guarantees | Architecture | Specify version-qualified evidence anchors | Define source ID, revision, digest, exact span, extractor provenance and stable resolution behavior. | Anchor contract and JSON schema | In Progress | Medium | 06.01;05.03 |  |  | Prior implementation or draft; verification required
06.03 | 6 | Formal evidence model and guarantees | Architecture | Specify retrieval admissibility predicate | Formalize project, access, source-version and historical cutoff eligibility, including graph expansions. | Admissibility rules and proofs/obligations | In Progress | Medium | 06.02 |  |  | Prior implementation or draft; verification required
06.04 | 6 | Formal evidence model and guarantees | Architecture | Specify atomic claim-support semantics | Define supported, refuted, mixed, insufficient and unverified states; distinguish relevance from entailment. | Claim judgment rubric and contract | In Progress | Medium | 06.02;03.02 |  |  | Prior implementation or draft; verification required
06.05 | 6 | Formal evidence model and guarantees | Architecture | Specify review authorization state machine | Define proposed/reviewed/accepted/rejected/deferred transitions, identity, role checks and immutable audit. | Finding lifecycle specification | In Progress | Medium | 06.04;05.08 |  |  | Prior implementation or draft; verification required
06.06 | 6 | Formal evidence model and guarantees | Architecture | Write architecture conformance tests | Build positive/negative fixtures for invalid edges, stale anchors, unauthorized access and wrong-time evidence. | Automated invariant test suite | Not Started | Medium | 06.01;06.03;06.05 |  |  | Planned / not evidenced
06.07 | 6 | Formal evidence model and guarantees | Architecture | Test source changes and adversarial evidence | Modify source versions, revoke access, inject misleading citations and conflicting passages; measure invariant failures. | Adversarial conformance report | Not Started | Medium | 06.06 |  |  | Planned / not evidenced
06.08 | 6 | Formal evidence model and guarantees | Architecture | Document guarantees versus limitations | Separate enforceable software properties from unproved semantic correctness or certification guarantees. | Architecture assurance and limitations section | Not Started | Medium | 06.07 |  |  | Planned / not evidenced
07.01 | 7 | Retrieval, verification and AI pipeline | Engineering | Establish reproducible lexical retrieval | Index artifact versions and implement BM25 with project/access filters and stable result IDs. | BM25 baseline and tests | Not Started | Medium | 05.03;04.09 |  |  | Planned / not evidenced
07.02 | 7 | Retrieval, verification and AI pipeline | Engineering | Establish reproducible dense retrieval | Pin embedding model, chunk policy, similarity metric and vector index; log rebuild metadata. | Dense RAG baseline and index manifest | Not Started | Medium | 07.01 |  |  | Planned / not evidenced
07.03 | 7 | Retrieval, verification and AI pipeline | Engineering | Implement and tune hybrid fusion | Specify fusion and reranking, retrieval budget, tie-breaking and threshold selection using development data. | Hybrid retrieval service and tuning report | Not Started | Medium | 07.01;07.02 |  |  | Planned / not evidenced
07.04 | 7 | Retrieval, verification and AI pipeline | Engineering | Implement graph-aware retrieval | Traverse typed SEG relations with path constraints, cycle limits, provenance and relevance scoring. | Graph retrieval module and path traces | Not Started | Medium | 06.01;07.03 |  |  | Planned / not evidenced
07.05 | 7 | Retrieval, verification and AI pipeline | Engineering | Enforce access/version/time in every channel | Apply identical admissibility across lexical, vector, reranking, graph expansion and final evidence assembly. | Retrieval eligibility regression tests | Not Started | Medium | 06.03;07.04 |  |  | Planned / not evidenced
07.06 | 7 | Retrieval, verification and AI pipeline | Engineering | Implement grounded claim generation | Generate atomic safety claims with source anchors, uncertainty, abstention and structured machine-readable output. | Claim generation schema and prompts | Not Started | Medium | 07.05;06.04 |  |  | Planned / not evidenced
07.07 | 7 | Retrieval, verification and AI pipeline | Engineering | Implement claim verification and conflict detection | Independently evaluate whether eligible spans entail, contradict or fail to support each claim; retain rationales. | Verifier service and calibration dataset | Not Started | Medium | 07.06 |  |  | Planned / not evidenced
07.08 | 7 | Retrieval, verification and AI pipeline | Engineering | Evaluate prompt-injection and source manipulation | Test untrusted document instructions, citation laundering, contradictory evidence and hallucinated anchors. | Security and robustness test report | Not Started | Medium | 07.07 |  |  | Planned / not evidenced
07.09 | 7 | Retrieval, verification and AI pipeline | Engineering | Benchmark pipeline cost and latency | Measure ingestion, retrieval, generation, verification, reviewer time, tokens and memory under repeat runs. | Latency/cost performance profile | Not Started | Medium | 07.03;07.07 |  |  | Planned / not evidenced
08.01 | 8 | MCAS source corpus and evidence integrity | Case Study | Define MCAS case-study scope and periods | Identify aircraft/system boundaries, events, accident chronology and pre-/post-event analytical cutoffs. | MCAS study protocol and timeline | In Progress | Medium | 03.01 |  |  | Prior implementation or draft; verification required
08.02 | 8 | MCAS source corpus and evidence integrity | Case Study | Build authoritative source inventory | Catalog FAA, NTSB, JATR, congressional, certification and technical sources; distinguish public facts from reconstruction. | Source catalog with provenance | In Progress | Medium | 08.01 |  |  | Prior implementation or draft; verification required
08.03 | 8 | MCAS source corpus and evidence integrity | Case Study | Verify licensing, access and authenticity | Record source URLs, publication dates, versions, licensing and integrity hashes; avoid treating reconstructed material as original. | Source rights and integrity ledger | Not Started | Medium | 08.02 |  |  | Planned / not evidenced
08.04 | 8 | MCAS source corpus and evidence integrity | Case Study | Extract MCAS requirements and assumptions | Create source-linked requirements, sensor assumptions, control logic and operating envelopes with confidence/uncertainty tags. | Requirements and assumptions dataset | In Progress | Medium | 08.02 |  |  | Prior implementation or draft; verification required
08.05 | 8 | MCAS source corpus and evidence integrity | Case Study | Extract architecture and control interfaces | Represent AoA inputs, flight-control computation, trim actuator, pilot interaction and system boundaries. | MCAS architecture model and interface map | In Progress | Medium | 08.04 |  |  | Prior implementation or draft; verification required
08.06 | 8 | MCAS source corpus and evidence integrity | Case Study | Build hazard and safety-constraint inventory | Use STPA and published evidence to identify hazards, unsafe control actions, causal scenarios and constraints. | Adjudication-ready MCAS hazard log | In Progress | Medium | 08.04;08.05 |  |  | Prior implementation or draft; verification required
08.07 | 8 | MCAS source corpus and evidence integrity | Case Study | Build historical admissibility partitions | Separate evidence available at each cutoff from post-event findings; label retrospective-only evidence. | Time-sliced evidence corpus | Not Started | Medium | 08.02;06.03 |  |  | Planned / not evidenced
08.08 | 8 | MCAS source corpus and evidence integrity | Case Study | Map sources to SEG with precise anchors | Link requirements, components, hazards, controls, tests and incident evidence using typed and versioned assertions. | MCAS SEG import package | Not Started | Medium | 08.03;08.06;06.02 |  |  | Planned / not evidenced
08.09 | 8 | MCAS source corpus and evidence integrity | Case Study | Independent domain review of MCAS dataset | Have experts audit claims, contested interpretations, source citations and scenario labels; record disagreement. | Adjudicated MCAS evidence baseline | Not Started | Medium | 08.07;08.08 |  |  | Planned / not evidenced
09.01 | 9 | MCAS simulator and fault-injection platform | Case Study | Audit existing modular MCAS Java reactor | Confirm simulator modules, Java package conventions, reproducible Maven build, tests and currently working scenarios. | Simulator code audit and build manifest | Implemented—Verify | Medium | 04.02;08.01 |  |  | Prior implementation or draft; verification required
09.02 | 9 | MCAS simulator and fault-injection platform | Case Study | Freeze flight-control model assumptions | Document simplified pitch, stabilizer, AoA sensing, pilot actions and limitations relative to real aircraft. | Simulator assumptions and model card | In Progress | Medium | 09.01;08.05 |  |  | Prior implementation or draft; verification required
09.03 | 9 | MCAS simulator and fault-injection platform | Case Study | Define nominal reference scenarios | Specify stable/nominal operation and expected signals, units, event timing and baseline acceptance criteria. | Nominal scenario fixtures | In Progress | Medium | 09.02 |  |  | Prior implementation or draft; verification required
09.04 | 9 | MCAS simulator and fault-injection platform | Case Study | Implement and test sensor fault injections | Cover biased/stuck/noisy/disagreeing AoA and temporal fault sequences with repeatable seeds. | Fault injection suite | Implemented—Verify | Medium | 09.03 |  |  | Prior implementation or draft; verification required
09.05 | 9 | MCAS simulator and fault-injection platform | Case Study | Implement pilot and monitoring responses | Exercise pilot workload, recognition, corrective actions, safety monitor interventions and detection thresholds. | Human/monitor simulation tests | Implemented—Verify | Medium | 09.04 |  |  | Prior implementation or draft; verification required
09.06 | 9 | MCAS simulator and fault-injection platform | Case Study | Implement unsafe-control and hazard scenarios | Map model behavior to explicit unsafe control actions, hazardous states and severity criteria. | Scenario catalog and hazard labels | In Progress | Medium | 09.04;08.06 |  |  | Prior implementation or draft; verification required
09.07 | 9 | MCAS simulator and fault-injection platform | Case Study | Validate simulator against published constraints | Check qualitative behavior and trace consistency with credible sources; disclose fidelity limits. | Simulator validation report | Not Started | Medium | 09.05;09.06 |  |  | Planned / not evidenced
09.08 | 9 | MCAS simulator and fault-injection platform | Case Study | Export reproducible simulation evidence | Emit structured event traces, parameters, seeds, hashes, manifests and stable evidence IDs. | Versioned simulation evidence package | Not Started | Medium | 09.07;04.09 |  |  | Planned / not evidenced
09.09 | 9 | MCAS simulator and fault-injection platform | Case Study | Test corrective-control alternatives | Compare sensor voting, authority limits, pilot override, monitoring and procedural mitigations under matched faults. | Corrective-action scenario results | Not Started | Medium | 09.08 |  |  | Planned / not evidenced
10.01 | 10 | MCAS-to-SafetyRAG integration | Integration | Define integration artifact mapping | Map simulator requirements, events, failures, controls and tests to SafetyRAG entities and SEG relationships. | Integration mapping specification | In Progress | Medium | 08.08;09.08 |  |  | Prior implementation or draft; verification required
10.02 | 10 | MCAS-to-SafetyRAG integration | Integration | Implement import schema and integrity checks | Validate manifests, source hashes, schema versions, visibility and stable identities before accepting data. | MCAS import contract and validator | Not Started | Medium | 10.01 |  |  | Planned / not evidenced
10.03 | 10 | MCAS-to-SafetyRAG integration | Integration | Implement project-scoped import adapter | Load MCAS packages into Spring Boot project, documents, evidence, requirements and SEG without duplicates. | Idempotent import API/CLI | Not Started | Medium | 10.02;05.10 |  |  | Planned / not evidenced
10.04 | 10 | MCAS-to-SafetyRAG integration | Integration | Preserve simulator provenance and time scope | Keep scenario IDs, seed, code revision, timestamp, event order, source provenance and historical eligibility. | Integrated provenance records | Not Started | Medium | 10.03;06.03 |  |  | Planned / not evidenced
10.05 | 10 | MCAS-to-SafetyRAG integration | Integration | Build MCAS analysis workflows | Allow safety engineer to retrieve scenario evidence, run hazard/control analysis, inspect support and submit review. | Integrated case-study UI and APIs | Not Started | Medium | 10.03;07.07 |  |  | Planned / not evidenced
10.06 | 10 | MCAS-to-SafetyRAG integration | Integration | Run end-to-end integration regression | Test nominal and faulty scenarios from simulation through ingestion, SEG, retrieval, findings and review. | MCAS integration acceptance report | Not Started | Medium | 10.04;10.05 |  |  | Planned / not evidenced
10.07 | 10 | MCAS-to-SafetyRAG integration | Integration | Freeze evaluation-ready integrated release | Tag all components, export database/index manifests and archive exact corpus used in experiments. | MCAS/SafetyRAG reproducible release | Not Started | Medium | 10.06 |  |  | Planned / not evidenced
11.01 | 11 | Gold standards and benchmark construction | Evaluation | Define benchmark task taxonomy | Include hazard detection, unsafe requirements, missing controls, evidence retrieval, path tracing, contradictions and temporal cutoff queries. | Benchmark task specification | Not Started | High | 03.02;08.06 |  |  | Planned / not evidenced
11.02 | 11 | Gold standards and benchmark construction | Evaluation | Sample MCAS queries without hindsight leakage | Generate representative, difficult and negative cases from pre-defined source partitions and risk categories. | Balanced benchmark question bank | Not Started | High | 11.01;08.07 |  |  | Planned / not evidenced
11.03 | 11 | Gold standards and benchmark construction | Evaluation | Construct evidence relevance labels | Mark exact supporting/refuting spans, required paths and acceptable alternate evidence; define ambiguous cases. | Gold relevance/path dataset | Not Started | High | 11.02 |  |  | Planned / not evidenced
11.04 | 11 | Gold standards and benchmark construction | Evaluation | Construct hazard and claim labels | Adjudicate true hazards, missing controls, unsupported claims and severity with independent domain experts. | Gold hazard/claim dataset | Not Started | High | 11.02;08.09 |  |  | Planned / not evidenced
11.05 | 11 | Gold standards and benchmark construction | Evaluation | Train annotators and measure agreement | Provide coding handbook, blinded practice cases, adjudication rules and inter-rater reliability. | Annotation guide and agreement report | Not Started | High | 11.03;11.04 |  |  | Planned / not evidenced
11.06 | 11 | Gold standards and benchmark construction | Evaluation | Separate development and held-out test sets | Prevent tuning and prompt selection on test data; version all splits and leakage checks. | Frozen train/dev/test manifests | Not Started | High | 11.05 |  |  | Planned / not evidenced
11.07 | 11 | Gold standards and benchmark construction | Evaluation | Build automated scoring and audit scripts | Implement metric computations, uncertainty estimates, per-query errors and artifact-level provenance checks. | Benchmark runner and metric tests | Not Started | High | 03.03;11.06 |  |  | Planned / not evidenced
11.08 | 11 | Gold standards and benchmark construction | Evaluation | Publish benchmark data access policy | Determine public, restricted and synthetic portions; supply licenses, ethics constraints and redaction decisions. | Dataset card and sharing plan | Not Started | High | 11.07 |  |  | Planned / not evidenced
12.01 | 12 | System evaluation and ablation experiments | Evaluation | Reproduce LLM-only and conventional RAG baselines | Establish comparable prompting, retrieval, budgets and runtime; retain all raw outputs. | Baseline run archive | Not Started | High | 11.07;07.09 |  |  | Planned / not evidenced
12.02 | 12 | System evaluation and ablation experiments | Evaluation | Implement REFSafE-inspired strong baseline | Reproduce work-scope extraction, hybrid search/reranking, incident hazard inference and policy matching as feasible; label as inspired unless faithful. | REFSafE-inspired baseline specification and code | Not Started | High | 02.03;11.07 |  |  | Planned / not evidenced
12.03 | 12 | System evaluation and ablation experiments | Evaluation | Evaluate SEG versus non-graph retrieval | Compare exact evidence recall, relation-path recall, traceability completeness and latency under matched settings. | RQ1/RQ2 graph ablation results | Not Started | High | 12.01;12.02;07.04 |  |  | Planned / not evidenced
12.04 | 12 | System evaluation and ablation experiments | Evaluation | Evaluate version and time eligibility | Inject old/new versions and future evidence; test leakage, anchor resolution and incorrect historical answers. | Temporal/provenance experiment results | Not Started | High | 06.07;11.07;12.03 |  |  | Planned / not evidenced
12.05 | 12 | System evaluation and ablation experiments | Evaluation | Evaluate claim verification effects | Measure supported/refuted/insufficient classification, unsupported output rate, abstention and severity-weighted errors. | RQ3 verification ablation results | Not Started | High | 07.07;11.04;12.03 |  |  | Planned / not evidenced
12.06 | 12 | System evaluation and ablation experiments | Evaluation | Evaluate complete pipeline and tradeoffs | Compare full SafetyRAG with ablations across quality, runtime, compute cost and failure modes. | Integrated system comparison | Not Started | High | 12.03;12.04;12.05 |  |  | Planned / not evidenced
12.07 | 12 | System evaluation and ablation experiments | Evaluation | Run repeated trials and sensitivity checks | Vary seeds, model versions, k, thresholds, corpus splits and prompts; estimate uncertainty. | Robustness and sensitivity appendix | Not Started | High | 12.06 |  |  | Planned / not evidenced
12.08 | 12 | System evaluation and ablation experiments | Evaluation | Perform qualitative failure analysis | Categorize wrong sources, false confidence, missed hazards, graph errors and reviewer burden with concrete examples. | Error taxonomy and case narratives | Not Started | High | 12.07 |  |  | Planned / not evidenced
12.09 | 12 | System evaluation and ablation experiments | Evaluation | Freeze confirmatory outputs and analysis | Archive raw traces, metric scripts, tables, figures and protocol deviations; independently verify calculations. | Reproducible evaluation bundle | Not Started | High | 12.08 |  |  | Planned / not evidenced
13.01 | 13 | Secondary case and generalization | Evaluation | Select secondary safety-critical case | Choose domain based on access, artifact diversity, expert availability, ethical constraints and transfer difficulty. | Secondary case selection memo | Not Started | High | 03.01;12.03 |  |  | Planned / not evidenced
13.02 | 13 | Secondary case and generalization | Evaluation | Acquire and verify secondary corpus | Build source register, versions, legal/ethical access and temporal partitions without reusing MCAS-specific shortcuts. | Secondary case evidence corpus | Not Started | High | 13.01 |  |  | Planned / not evidenced
13.03 | 13 | Secondary case and generalization | Evaluation | Construct secondary-case SEG and labels | Annotate requirements, hazards, controls, paths, claims and gold references with independent review. | Secondary gold standard | Not Started | High | 13.02;11.05 |  |  | Planned / not evidenced
13.04 | 13 | Secondary case and generalization | Evaluation | Run fixed-protocol transfer evaluation | Apply frozen SafetyRAG and baselines with minimal retuning; compare error types and effect sizes. | RQ5 generalization results | Not Started | High | 12.09;13.03 |  |  | Planned / not evidenced
13.05 | 13 | Secondary case and generalization | Evaluation | Report boundaries of generalization | Explain domain differences, transfer failures, data availability and which mechanisms are reusable. | Cross-case synthesis | Not Started | High | 13.04 |  |  | Planned / not evidenced
14.01 | 14 | Human-subject study preparation | Human Study | Specify human-study decision tasks | Choose realistic artifact review, hazard acceptance, evidence adjudication and conflicting-evidence scenarios. | Human task scenarios and rubric | Not Started | Medium | 11.04;12.06 |  |  | Planned / not evidenced
14.02 | 14 | Human-subject study preparation | Human Study | Define conditions and allocation | Compare human alone, AI recommendations, evidence/provenance, and verification/uncertainty; control learning/order effects. | Experimental design and randomization plan | Not Started | Medium | 14.01 |  |  | Planned / not evidenced
14.03 | 14 | Human-subject study preparation | Human Study | Plan recruitment and sample size | Define engineer expertise, eligibility, recruitment channels, power/precision, compensation and inclusion rules. | Recruitment and sample-size rationale | Not Started | Medium | 14.02 |  |  | Planned / not evidenced
14.04 | 14 | Human-subject study preparation | Human Study | Prepare consent, privacy and risk materials | Document data handling, participant rights, retention, de-identification, security and any model-data exposure. | Consent forms and data protection plan | Not Started | Medium | 14.03 |  |  | Planned / not evidenced
14.05 | 14 | Human-subject study preparation | Human Study | Submit IRB/ethics determination | Obtain institutional approval or exemption determination before recruiting or collecting participant data. | IRB approval/exemption record | Not Started | Medium | 14.04;01.08 |  |  | Planned / not evidenced
14.06 | 14 | Human-subject study preparation | Human Study | Build instrumented study interface | Log task outcomes, evidence views, model advice, acceptance changes, timestamps and NASA-TLX/trust measures. | Human-study UI and logging package | Not Started | Medium | 14.02;10.06 |  |  | Planned / not evidenced
14.07 | 14 | Human-subject study preparation | Human Study | Pilot usability and task difficulty | Conduct approved pilots, identify ambiguous tasks, excessive duration and interface confounds; amend protocol if needed. | Pilot study report and revisions | Not Started | Medium | 14.05;14.06 |  |  | Planned / not evidenced
14.08 | 14 | Human-subject study preparation | Human Study | Freeze human-study protocol and training | Standardize instructions, practice tasks, counterbalancing and experimenter scripts. | Locked study protocol and materials | Not Started | Medium | 14.07 |  |  | Planned / not evidenced
15.01 | 15 | Human-subject execution and analysis | Human Study | Recruit and screen participants | Enroll eligible safety engineers or justified proxies after ethics authorization; track exclusions. | De-identified participant roster | Not Started | Medium | 14.08 |  |  | Planned / not evidenced
15.02 | 15 | Human-subject execution and analysis | Human Study | Run controlled study sessions | Execute randomized conditions, monitor protocol adherence, preserve raw logs and document deviations. | Human experiment session archive | Not Started | Medium | 15.01 |  |  | Planned / not evidenced
15.03 | 15 | Human-subject execution and analysis | Human Study | Score safety decisions independently | Blindly adjudicate correctness, false negatives, inappropriate acceptance, missed contradictions and time. | Human decision outcome dataset | Not Started | Medium | 15.02 |  |  | Planned / not evidenced
15.04 | 15 | Human-subject execution and analysis | Human Study | Measure workload, trust and reliance | Compute NASA-TLX, trust calibration, acceptance/rejection patterns and over-/under-reliance. | Human factors metrics dataset | Not Started | Medium | 15.02 |  |  | Planned / not evidenced
15.05 | 15 | Human-subject execution and analysis | Human Study | Analyze RQ4 and subgroup sensitivity | Apply predeclared paired/mixed analyses, intervals and sensitivity to expertise/order effects. | Human-study statistical results | Not Started | Medium | 15.03;15.04 |  |  | Planned / not evidenced
15.06 | 15 | Human-subject execution and analysis | Human Study | Document ethical and external validity limits | Explain participant representativeness, task realism, learning effects, interface bias and risks of automation. | Human-study limitations and audit | Not Started | Medium | 15.05 |  |  | Planned / not evidenced
16.01 | 16 | Architecture and design paper (EMSE) | Publication | Freeze paper contribution and claims | Position SafetyRAG relative to REFSafE and graph/safety RAG; distinguish implemented, specified and experimentally tested features. | EMSE claim/evidence outline | In Progress | Medium | 02.08;06.08 |  |  | Prior implementation or draft; verification required
16.02 | 16 | Architecture and design paper (EMSE) | Publication | Finalize research questions and paper scope | Choose architecture and system-level empirical questions; avoid promising a completed human study if not conducted. | Paper protocol and section outline | In Progress | Medium | 03.01;16.01 |  |  | Prior implementation or draft; verification required
16.03 | 16 | Architecture and design paper (EMSE) | Publication | Prepare architecture diagrams and formal model | Produce SEG schema, retrieval/verification flow, version/admissibility contracts and review lifecycle diagrams. | Publication-quality figures and formal definitions | In Progress | Medium | 06.08;16.02 |  |  | Prior implementation or draft; verification required
16.04 | 16 | Architecture and design paper (EMSE) | Publication | Implement and validate publishable system slice | Ensure essential mechanisms work end to end, conformance tests pass and exact code version is archived. | Paper artifact release and tests | Not Started | Medium | 10.07;07.08 |  |  | Planned / not evidenced
16.05 | 16 | Architecture and design paper (EMSE) | Publication | Execute controlled retrieval/verification studies | Collect baseline, ablation, MCAS evidence and statistical results for manuscript claims. | Experimental result tables and figures | Not Started | Medium | 12.09;16.04 |  |  | Planned / not evidenced
16.06 | 16 | Architecture and design paper (EMSE) | Publication | Write full introduction and related work | Explain problem, research gap, prior-art comparison, hypotheses and bounded novelty with checked citations. | Introduction and related-work draft | In Progress | Medium | 02.10;16.01 |  |  | Prior implementation or draft; verification required
16.07 | 16 | Architecture and design paper (EMSE) | Publication | Write methods, implementation and threats | Provide datasets, model settings, algorithms, metrics, controls, limitations and reproducibility details. | Methods and validity sections | Not Started | Medium | 16.03;16.05 |  |  | Planned / not evidenced
16.08 | 16 | Architecture and design paper (EMSE) | Publication | Write results, discussion and conclusions | Report effect sizes and uncertainty, null results, failures, practical implications and unsupported assumptions. | Complete results-driven manuscript | Not Started | Medium | 16.05;16.07 |  |  | Planned / not evidenced
16.09 | 16 | Architecture and design paper (EMSE) | Publication | Run internal critical review and revise | Get adviser/coauthor and independent reviewer critique; verify all tables, references, novelty and journal requirements. | Submission-ready revised manuscript | Not Started | Medium | 16.08 |  |  | Planned / not evidenced
16.10 | 16 | Architecture and design paper (EMSE) | Publication | Prepare EMSE submission package | Follow current author guide, format manuscript, anonymize if required, complete ethics/data statements, cover letter and supplementary materials. | Manuscript, cover letter, data/code package | Not Started | Medium | 16.09 |  |  | Planned / not evidenced
16.11 | 16 | Architecture and design paper (EMSE) | Publication | Submit paper and preserve submission record | Upload to journal, validate generated PDF and archive submission ID and exact submitted files. | EMSE submission receipt | Not Started | Medium | 16.10 |  |  | Planned / not evidenced
16.12 | 16 | Architecture and design paper (EMSE) | Publication | Address editorial and peer review | Respond point-by-point, rerun analyses if needed, update code/data and track versioned revisions. | Response letter and revised manuscript | Not Started | Medium | 16.11 |  |  | Planned / not evidenced
16.13 | 16 | Architecture and design paper (EMSE) | Publication | Complete acceptance, proofs and dissemination | Review proofs, archive DOI, publish permitted artifacts and update dissertation bibliography. | Accepted/published article and repository record | Not Started | Medium | 16.12 |  |  | Planned / not evidenced
17.01 | 17 | Further research publications | Publication | Plan retrieval/provenance empirical paper | Define distinct research question, corpus, metrics and novelty relative to architecture paper; avoid duplicate publication. | Retrieval/provenance paper plan | Not Started | Medium | 12.09;16.01 |  |  | Planned / not evidenced
17.02 | 17 | Further research publications | Publication | Draft retrieval/provenance manuscript | Write related work, precise methods, temporal/anchor tests, statistical findings and replication materials. | Second manuscript complete draft | Not Started | Medium | 17.01 |  |  | Planned / not evidenced
17.03 | 17 | Further research publications | Publication | Submit and revise retrieval paper | Select appropriate venue, check overlap, submit, respond to reviews and preserve artifacts. | Second paper submission/publication record | Not Started | Medium | 17.02 |  |  | Planned / not evidenced
17.04 | 17 | Further research publications | Publication | Plan MCAS hazard analysis case-study paper | Focus on simulation fidelity, fault scenarios, corrective controls, historical validity and expert adjudication. | MCAS case-study paper plan | Not Started | Medium | 09.09;12.09 |  |  | Planned / not evidenced
17.05 | 17 | Further research publications | Publication | Draft and submit MCAS study | Write case context, model assumptions, simulation protocol, empirical findings and limitations; handle review cycle. | MCAS manuscript and submission record | Not Started | Medium | 17.04 |  |  | Planned / not evidenced
17.06 | 17 | Further research publications | Publication | Plan human-AI teaming paper | Define human-decision novelty, ethics, experimental contrasts and outcomes distinct from system architecture. | Human-study paper plan | Not Started | Medium | 15.06 |  |  | Planned / not evidenced
17.07 | 17 | Further research publications | Publication | Draft and submit human study | Report participant design, measures, statistical findings, limitations and replicable instruments. | Human-AI paper and submission record | Not Started | Medium | 17.06 |  |  | Planned / not evidenced
17.08 | 17 | Further research publications | Publication | Evaluate optional cross-domain synthesis paper | Proceed only if secondary case yields independent findings and sufficient contribution. | Optional generalization paper decision | Not Started | Medium | 13.05 |  |  | Planned / not evidenced
17.09 | 17 | Further research publications | Publication | Maintain publication ethics and authorship | Document authorship, overlap, permissions, artifact releases, conference/journal policy and preprint choices. | Authorship and publication compliance log | In Progress | Medium | 16.01 |  |  | Prior implementation or draft; verification required
18.01 | 18 | Dissertation drafting and integration | Dissertation | Confirm graduate-school dissertation rules | Verify dissertation format, committee requirements, manuscript integration policy, repository submission and required forms. | Institutional dissertation compliance checklist | Needs Verification | High | 01.08 |  |  | Prior implementation or draft; verification required
18.02 | 18 | Dissertation drafting and integration | Dissertation | Reconcile existing LaTeX chapter drafts | Inventory drafted chapters, references, figures and stale claims; mark placeholders and obsolete architectures. | Chapter inventory and revision backlog | In Progress | High | 18.01;02.10 |  |  | Prior implementation or draft; verification required
18.03 | 18 | Dissertation drafting and integration | Dissertation | Write Chapter 1: introduction and problem | State motivation, precise gap, RQs, contributions, scope and organization, reflecting REFSafE. | Chapter 1 final draft | In Progress | High | 03.01;18.02 |  |  | Prior implementation or draft; verification required
18.04 | 18 | Dissertation drafting and integration | Dissertation | Write Chapter 2: foundations and related work | Integrate systematic literature, safety theory, REFSafE comparison and bounded novelty. | Chapter 2 final draft | In Progress | High | 02.10;18.02 |  |  | Prior implementation or draft; verification required
18.05 | 18 | Dissertation drafting and integration | Dissertation | Write Chapter 3: SafetyRAG architecture | Present SEG, provenance, retrieval, verification, authorization, formal requirements and design tradeoffs. | Chapter 3 final draft | In Progress | High | 06.08;18.02 |  |  | Prior implementation or draft; verification required
18.06 | 18 | Dissertation drafting and integration | Dissertation | Write Chapter 4: methodology and benchmark | Specify case studies, data provenance, gold standards, experimental controls, metrics and statistics. | Chapter 4 final draft | Not Started | High | 11.08;03.08 |  |  | Planned / not evidenced
18.07 | 18 | Dissertation drafting and integration | Dissertation | Write Chapter 5: MCAS system and experiments | Describe simulator, scenario validity, integrated SafetyRAG workflow and case-study data. | Chapter 5 final draft | Not Started | High | 10.07;09.09 |  |  | Planned / not evidenced
18.08 | 18 | Dissertation drafting and integration | Dissertation | Write Chapter 6: technical empirical results | Present controlled system comparisons, ablations, failure analysis, uncertainty and reproducibility. | Chapter 6 final draft | Not Started | High | 12.09 |  |  | Planned / not evidenced
18.09 | 18 | Dissertation drafting and integration | Dissertation | Write Chapter 7: human and generalization results | Present human-study and secondary-case findings, or document approved scope adjustments. | Chapter 7 final draft | Not Started | High | 13.05;15.06 |  |  | Planned / not evidenced
18.10 | 18 | Dissertation drafting and integration | Dissertation | Write Chapter 8: synthesis and conclusions | Integrate findings by RQ, theoretical/practical contributions, threats, future work and limitations. | Chapter 8 final draft | Not Started | High | 18.06;18.07;18.08 |  |  | Planned / not evidenced
18.11 | 18 | Dissertation drafting and integration | Dissertation | Prepare appendices and artifact catalog | Include protocols, detailed schemas, prompts, code manifests, source registers, instruments and supplementary results. | Complete dissertation appendices | Not Started | High | 18.09 |  |  | Planned / not evidenced
18.12 | 18 | Dissertation drafting and integration | Dissertation | Audit dissertation claims and citations | Check every empirical claim against tables/data, every source against reference manager and no unmeasured superiority claims. | Claim-to-evidence audit report | Not Started | High | 18.10 |  |  | Planned / not evidenced
18.13 | 18 | Dissertation drafting and integration | Dissertation | Complete adviser and committee revisions | Run chapter reviews, resolve tracked comments, language consistency, figures and cross-references. | Committee-review dissertation draft | Not Started | High | 18.11 |  |  | Planned / not evidenced
19.01 | 19 | Defense, submission and archival | Graduation | Verify eligibility to schedule defense | Confirm approval milestones, enrollment, publication requirements if any, committee availability and university deadlines. | Defense eligibility confirmation | Not Started | High | 18.12;01.08 |  |  | Planned / not evidenced
19.02 | 19 | Defense, submission and archival | Graduation | Prepare defense slide deck and script | Condense methods, implementation, results, validity, contributions and REFSafE positioning into defensible narrative. | Defense presentation and speaking notes | Not Started | High | 19.01 |  |  | Planned / not evidenced
19.03 | 19 | Defense, submission and archival | Graduation | Conduct mock defense and adversarial Q&A | Practice novelty, baseline fairness, ethics, MCAS hindsight, reproducibility and negative-result explanations. | Mock defense critique and revised materials | Not Started | High | 19.02 |  |  | Planned / not evidenced
19.04 | 19 | Defense, submission and archival | Graduation | Distribute dissertation to committee | Send approved draft and supporting artifacts with required lead time; document receipt and changes. | Committee circulation record | Not Started | High | 19.01;18.12 |  |  | Planned / not evidenced
19.05 | 19 | Defense, submission and archival | Graduation | Complete oral dissertation defense | Present research and answer committee questions; record outcome and conditions. | Defense decision and revision list | Not Started | High | 19.03;19.04 |  |  | Planned / not evidenced
19.06 | 19 | Defense, submission and archival | Graduation | Complete post-defense corrections | Implement required revisions, secure approvals and independently validate all references and figures. | Approved final dissertation | Not Started | High | 19.05 |  |  | Planned / not evidenced
19.07 | 19 | Defense, submission and archival | Graduation | Submit final dissertation to repository | Follow institutional ETD formatting, embargo and metadata policies; archive accepted submission. | Final ETD submission confirmation | Not Started | High | 19.06 |  |  | Planned / not evidenced
19.08 | 19 | Defense, submission and archival | Graduation | Archive reproducibility package | Release permitted code, synthetic/restricted data instructions, checksums, model configs, protocols and persistent identifiers. | Versioned research archive and DOI | Not Started | High | 19.06;12.09 |  |  | Planned / not evidenced
19.09 | 19 | Defense, submission and archival | Graduation | Complete final administrative clearance | Confirm graduation forms, signatures, library deposit and program requirements. | Degree completion clearance | Not Started | High | 19.07;19.08 |  |  | Planned / not evidenced
20.01 | 20 | Ongoing research management and quality | Management | Maintain living master checklist | Update task status only with evidence, record blockers and link outputs; review after each milestone. | Current master workbook and change history | In Progress | Medium | 01.01 |  |  | Prior implementation or draft; verification required
20.02 | 20 | Ongoing research management and quality | Management | Maintain research decision log | Record architectural choices, rejected alternatives, tradeoffs, scope changes and committee decisions. | Architecture/research decision records | In Progress | Medium | 20.01 |  |  | Prior implementation or draft; verification required
20.03 | 20 | Ongoing research management and quality | Management | Maintain source and citation integrity | Continuously check references, links, source dates, source hashes and claim-to-evidence mappings. | Citation/source audit ledger | In Progress | Medium | 02.02 |  |  | Prior implementation or draft; verification required
20.04 | 20 | Ongoing research management and quality | Management | Maintain backup and disaster recovery | Back up source, PostgreSQL, documents, experiment outputs and manuscript; test restoration. | Backup policy and restoration test | Needs Verification | Medium | 04.05 |  |  | Prior implementation or draft; verification required
20.05 | 20 | Ongoing research management and quality | Management | Maintain risk and blocker register | Track access, ethics, gold-standard availability, technical debt, model drift and schedule dependencies. | Risk register with mitigations | Not Started | Medium | 20.01 |  |  | Planned / not evidenced
20.06 | 20 | Ongoing research management and quality | Management | Review reproducibility at each milestone | Repeat fresh-machine setup and key benchmark smoke tests before freezing any result or publication. | Reproducibility gate reports | Not Started | Medium | 04.08;20.01 |  |  | Planned / not evidenced
20.07 | 20 | Ongoing research management and quality | Management | Document AI assistance and research integrity | Record LLM use in coding/writing/annotation, human validation, data handling and disclosure policy. | AI-use and integrity statement | Not Started | Medium | 20.01 |  |  | Planned / not evidenced
20.08 | 20 | Ongoing research management and quality | Management | Close project and hand off artifacts | Document final maintenance, access revocation, preservation, future research and repository ownership. | Project closeout and handover package | Not Started | Medium | 19.09 |  |  | Planned / not evidenced

## Phase Roadmap
Phase # | Phase / milestone | Workstream | Total tasks | Completed | In progress | Implemented / verify | Needs verification | Not started | Blocked | Completion % | Phase entry dependency | Phase exit / gate
1 | Research governance and approval | Governance | 9 | 0 | 3 | 0 | 3 | 2 | 0 | 0% |  | Research change log
2 | Prior art, novelty and theory | Literature | 10 | 0 | 7 | 0 | 0 | 2 | 0 | 0% | 01.03 | Versioned literature review dataset
3 | Research questions, hypotheses and measurement | Methodology | 9 | 0 | 2 | 0 | 0 | 7 | 0 | 0% | 01.08;02.08 | Stage-gate acceptance checklist
4 | Repository, infrastructure and reproducibility | Engineering | 9 | 0 | 3 | 0 | 0 | 6 | 0 | 0% | 01.01 | Machine-readable run manifest
5 | SafetyRAG core platform completion | Engineering | 10 | 0 | 0 | 7 | 0 | 3 | 0 | 0% | 04.03;04.05 | End-to-end acceptance report and demo
6 | Formal evidence model and guarantees | Architecture | 8 | 0 | 5 | 0 | 0 | 3 | 0 | 0% | 02.05;05.05 | Architecture assurance and limitations section
7 | Retrieval, verification and AI pipeline | Engineering | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0% | 05.03;04.09 | Latency/cost performance profile
8 | MCAS source corpus and evidence integrity | Case Study | 9 | 0 | 5 | 0 | 0 | 4 | 0 | 0% | 03.01 | Adjudicated MCAS evidence baseline
9 | MCAS simulator and fault-injection platform | Case Study | 9 | 0 | 3 | 3 | 0 | 3 | 0 | 0% | 04.02;08.01 | Corrective-action scenario results
10 | MCAS-to-SafetyRAG integration | Integration | 7 | 0 | 1 | 0 | 0 | 6 | 0 | 0% | 08.08;09.08 | MCAS/SafetyRAG reproducible release
11 | Gold standards and benchmark construction | Evaluation | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0% | 03.02;08.06 | Dataset card and sharing plan
12 | System evaluation and ablation experiments | Evaluation | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0% | 11.07;07.09 | Reproducible evaluation bundle
13 | Secondary case and generalization | Evaluation | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0% | 03.01;12.03 | Cross-case synthesis
14 | Human-subject study preparation | Human Study | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0% | 11.04;12.06 | Locked study protocol and materials
15 | Human-subject execution and analysis | Human Study | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | 14.08 | Human-study limitations and audit
16 | Architecture and design paper (EMSE) | Publication | 13 | 0 | 4 | 0 | 0 | 9 | 0 | 0% | 02.08;06.08 | Accepted/published article and repository record
17 | Further research publications | Publication | 9 | 0 | 1 | 0 | 0 | 8 | 0 | 0% | 12.09;16.01 | Authorship and publication compliance log
18 | Dissertation drafting and integration | Dissertation | 13 | 0 | 4 | 0 | 1 | 8 | 0 | 0% | 01.08 | Committee-review dissertation draft
19 | Defense, submission and archival | Graduation | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0% | 18.12;01.08 | Degree completion clearance
20 | Ongoing research management and quality | Management | 8 | 0 | 3 | 0 | 1 | 4 | 0 | 0% | 01.01 | Project closeout and handover package

## Publication Pipeline
Paper ID | Paper / contribution | Target venue | Current evidence-based assessment | Related task IDs | Scientific prerequisites | Complete publication workflow | Planning status
P1 | SafetyRAG architecture / formal model | Empirical Software Engineering (target) | Draft architecture/novelty analysis exists; empirical results not complete | 16.01–16.13 | 12.09;16.04 | Design + implementation + ablations + reproducibility + submission + revisions | Not Started
P2 | Retrieval, provenance and temporal eligibility | Venue to select | Distinct empirical manuscript not yet drafted | 17.01–17.03 | 12.09;17.01 | Gold standard + controlled retrieval and temporal experiments + paper + reviews | Not Started
P3 | MCAS safety case and corrective actions | Venue to select | Simulator and case materials partly developed; validated study outstanding | 17.04–17.05 | 09.09;12.09 | Validated simulator + hazards + controls + comparisons + paper + reviews | Not Started
P4 | Human–AI decision quality | Venue to select | Human study pending ethics, recruitment and experiments | 17.06–17.07 | 15.06 | IRB + study + analysis + human factors results + paper + reviews | Not Started
P5 | Cross-domain generalization (optional) | Venue to select | Secondary case not selected | 17.08 | 13.05 | Independent transfer study + manuscript only if results warrant | Deferred

## Status & Evidence Guide
Category | Definition / instructions
Purpose | Master dissertation checklist; tasks ordered by phase and linked with explicit prerequisite IDs. No fixed dates are required.
Completion rule | Only mark Completed (Verified) after checking an output and recording its location in column L, with supporting evidence in column M.
Completed (Artifact) | A deliverable exists (e.g., committee presentation), but approval/use of it is not implied.
Completed (Analysis) | A bounded analysis has been performed (e.g., REFSafE review), but full systematic review is not complete.
Implemented—Verify | A feature or milestone was described as implemented, but fresh-machine build, tests or end-to-end acceptance are not verified.
In Progress | Documented draft, partial code, or active work exists; acceptance criteria remain unmet.
Needs Verification | There may be prior progress, but status is not substantiated well enough to mark complete.
Not Started | No sufficient evidence of a completed task; some preliminary thinking may still exist.
Blocked | Cannot proceed due to a concrete unresolved prerequisite; document blocker in column N.
Deferred | Explicitly optional or postponed; do not count as completed.
Dependencies | Prerequisite task IDs are semicolon separated. Finish and verify all prerequisites before marking dependent task complete.
Evidence locations | Use paths, Git tags/commits, document filenames, DOI/URLs, committee records, IRB IDs or test report links.
Status baseline | As of 2026-10-29; conservative evidence-based reconstruction from earlier plans, source/code discussions and available artifacts.
Caveat | Not a repository audit, signed committee record, or complete systematic review. Status values require user confirmation and ongoing updates.
Source: development | Prior Java Spring Boot/PostgreSQL/React development records, build logs, milestone 13H and MCAS simulator discussions.
Source: research | Prior EMSE architecture manuscript, literature/REFSafE analysis, committee presentation, MCAS design, master plan and roadmap.
Recommended update cadence | After each completed milestone, committee meeting, experiment freeze, manuscript submission or software release.